## Requirements Stack
Requirement ID | Description | Story Points | Priority | Sprint No.
1 | As a developer, I want a shared GitHub repository with branch and pull request rules so that the team can work without overwriting each other | 2 | 1 | 1
2 | As a developer, I want a project skeleton with the chosen frontend, backend, and database so that everyone builds on the same base | 3 | 2 | 1
3 | As a developer, I want a cloud-hosted database and server so that roommates on different devices share the same data | 5 | 3 | 1
4 | As a new user, I want to register with my email and a password so that I have my own account | 5 | 4 | 1
5 | As a user, I want to log in and log out securely so that only I can access my account | 5 | 5 | 1
6 | As a user, I want my password stored hashed and salted so that it stays safe if data is leaked | 2 | 6 | 1
7 | As a roommate, I want to create a household so that my roommates and I have a shared space | 3 | 7 | 1
8 | As a roommate, I want to invite others with a code or link so that they can join my household | 5 | 8 | 1
9 | As a roommate, I want to join a household with an invite code so that I can see shared information | 3 | 9 | 1
10 | As a roommate, I want to see a home dashboard so that I can check balances, chores, and events at a glance | 5 | 10 | 1
11 | As a roommate, I want to add a shared expense with amount, description, date, and payer so that costs are tracked | 3 | 11 | 2
12 | As a roommate, I want to split an expense equally among selected roommates so that everyone pays a fair share | 3 | 12 | 2
13 | As a roommate, I want to split an expense by custom amounts or percentages so that uneven costs are handled | 5 | 13 | 2
14 | As a roommate, I want to see who owes whom so that I know my current balance | 5 | 14 | 2
15 | As a roommate, I want to record a payment so that a settled balance is cleared | 3 | 15 | 2
16 | As a roommate, I want to view the history of expenses so that I can review past spending | 2 | 16 | 2
17 | As a roommate, I want to edit or delete an expense so that mistakes can be fixed | 2 | 17 | 2
18 | As a roommate, I want to create a chore with an assignee and due date so that responsibilities are clear | 3 | 18 | 2
19 | As a roommate, I want to mark a chore complete so that others know it is done | 1 | 19 | 2
20 | As a roommate, I want to filter the chore list by roommate so that I can see my own tasks | 2 | 20 | 2
21 | As a roommate, I want to set chores to repeat daily, weekly, or monthly so that I do not re-enter them | 5 | 21 | 3
22 | As a roommate, I want to have chores rotate automatically so that work is shared fairly | 5 | 22 | 3
23 | As a roommate, I want to add and remove items on a shared grocery list so that we buy what the house needs | 3 | 23 | 2
24 | As a roommate, I want to check off grocery items as bought so that nobody buys duplicates | 1 | 24 | 2
25 | As a roommate, I want to see grocery list changes instantly on all devices so that the list is always current | 8 | 25 | 3
26 | As a roommate, I want to create house events such as guests, parties, and quiet hours so that everyone is informed | 5 | 26 | 3
27 | As a roommate, I want to view the house calendar by month and week so that I can plan ahead | 5 | 27 | 3
28 | As a roommate, I want to edit or delete calendar events so that the schedule stays accurate | 2 | 28 | 3
29 | As a user, I want forms to reject invalid amounts, dates, and missing fields so that bad data is not saved | 3 | 29 | 1
30 | As a user, I want clear error messages and helpful empty screens so that I know what to do next | 2 | 30 | 2
31 | As a user, I want the app to work on phone and desktop screens so that I can use it anywhere | 5 | 31 | 2
32 | As a user, I want a navigation menu so that I can move between expenses, chores, groceries, and calendar | 2 | 32 | 1
33 | As a user, I want a profile with my name, photo, and contact info so that roommates can recognize me | 3 | 33 | Backlog
34 | As a roommate, I want to rename or leave a household from settings so that I can manage my membership | 3 | 34 | 3
35 | As a household admin, I want to remove a roommate so that people who moved out lose access | 3 | 35 | 2
36 | As a household admin, I want admin and member roles so that only trusted users change settings | 5 | 36 | 2
37 | As a roommate, I want to get reminders before rent and utilities are due so that bills are paid on time | 5 | 37 | 4
38 | As a roommate, I want to set recurring expenses that repeat each month so that rent is added automatically | 5 | 38 | 4
39 | As a roommate, I want to get in-app notifications for new expenses, chores, and events so that I stay updated | 5 | 39 | 4
40 | As a roommate, I want to get emails about overdue chores and unpaid balances so that I do not forget | 5 | 40 | Backlog
41 | As a roommate, I want to attach a receipt photo to an expense so that others can verify the cost | 5 | 41 | Backlog
42 | As a developer, I want receipt images stored in cloud storage so that they load on any device | 3 | 42 | Backlog
43 | As a roommate, I want to scan a receipt so that the expense amount fills in automatically | 13 | 43 | Backlog
44 | As a roommate, I want to assign categories such as rent, utilities, and groceries so that spending is organized | 2 | 44 | 2
45 | As a roommate, I want to see monthly spending charts by category so that I understand where money goes | 8 | 45 | 4
46 | As a roommate, I want to turn purchased grocery items into a split expense so that shopping costs are shared | 5 | 46 | Backlog
47 | As a roommate, I want to add quantity and notes to grocery items so that the shopper buys the right thing | 1 | 47 | 2
48 | As a roommate, I want to see when quiet hours are active on the dashboard so that I respect them | 2 | 48 | 3
49 | As a roommate, I want to be notified when a guest visit is scheduled so that I am not surprised | 3 | 49 | Backlog
50 | As a roommate, I want to post notes on a house bulletin board so that I can share announcements | 5 | 50 | Backlog
51 | As a roommate, I want to comment on expenses and chores so that we can discuss them in the app | 5 | 51 | Backlog
52 | As a roommate, I want to search and filter expense history so that I can find a specific purchase | 3 | 52 | 3
53 | As a roommate, I want to export expense history to CSV so that I can keep my own records | 3 | 53 | 4
54 | As a roommate, I want to have debts simplified into the fewest payments so that settling up is easier | 8 | 54 | 3
55 | As a roommate, I want to earn points and see a leaderboard for chores so that doing them is more fun | 5 | 55 | Backlog
56 | As a user, I want a dark mode option so that the app is comfortable at night | 2 | 56 | 1
57 | As a user, I want to reset a forgotten password by email so that I can regain access to my account | 5 | 57 | 3
58 | As a user, I want two-factor authentication so that my account is harder to break into | 8 | 58 | Backlog
59 | As a user, I want privacy settings for my profile so that I control what roommates see | 3 | 59 | Backlog
60 | As a user, I want to delete my account and personal data so that my information is removed | 3 | 60 | Backlog
61 | As a household admin, I want a log of household changes so that I can see who changed what | 5 | 61 | 2
62 | As a developer, I want automated tests for the backend so that changes do not break features | 8 | 62 | 3
63 | As a developer, I want automated tests of the main user flows so that the interface stays working | 8 | 63 | Backlog
64 | As a developer, I want tests to run on every pull request so that broken code is caught early | 5 | 64 | 4
65 | As a developer, I want automatic linting and formatting checks so that code stays consistent | 2 | 65 | 4
66 | As a user with a disability, I want good contrast, labels, and keyboard navigation so that I can use the app | 5 | 66 | 4
67 | As a new user, I want a short onboarding tutorial so that I learn the app quickly | 3 | 67 | 4
68 | As a user, I want a help and FAQ page so that I can answer common questions myself | 1 | 68 | 4
69 | As a roommate, I want to track shared supplies with low-stock alerts so that we do not run out of essentials | 5 | 69 | Backlog
70 | As a roommate, I want to use a move-in and move-out checklist so that transitions go smoothly | 3 | 70 | Backlog
71 | As a user, I want to install the app on my phone and view data offline so that I can check it without signal | 13 | 71 | Backlog
72 | As a roomate, I want to open Venmo or PayPal from a balance so that I can pay a roommate quickly. | 8 | 72 | Backlog
73 | As a roommate, I want to link my bank account through Flinks so I can automatically settle what I owe in the app. | 13 | 73 | Backlog
74 | As a user, I want end-to-end encrypted messaging with my roomates so that these financial informations can be kept private. | 8 | 74 | Backlog
75 | As a user, I want a timeout after 20-30 minutes of inactivity so that my device remains secure. | 2 | 75 | 4
76 | As a student, I want to transfer my ownership of the household to another student so that management transitions smoothly when I move out. | 3 | 76 | Backlog
77 | As a roommate, I want a real-time indicator showing who is online or editing a shared list so that it avoids unnecessary conflicts or confusion among roommates. | 5 | 77 | Backlog
78 | As a user, I want to download a report of my personal data so that my records are maintained. | 3 | 78 | Backlog
79 | As a roommate, I want to attach my lease agreements and contracts to a secure household vault so that all official housing documents are readily available. | 3 | 79 | Backlog
80 | As a roomate, I would like to have an automatic system that calculates rent for individual move-in and move-out dates so that mid-month room transitions are fair to everyone. | 5 | 80 | Backlog
81 | As a developer, I want to prevent repeated logins and API requests so that attackers cannot guess the users' password or misuse their account. | 3 | 81 | 4
82 | As a roommate, I want to customize my notifications so that I only receive alerts that are relevant to my specififc chores and tasks. | 2 | 82 | Backlog
83 | As a developer, I want to allot automated daily cloud database backups with point-in-time recovery so that the financial data isn't lost. | 5 | 83 | Backlog
84 | As a roommate, I want a simple way to dispute shared expenses in the app so that any billing disagreements can be resolved fairly and transparently. | 5 | 84 | Backlog
85 | As a roomate, I would like to scan any barcodes on grocery items using my phone so that pantry inventory can be updated quickly. m | 8 | 85 | Backlog
86 | As a household, I want to create a shared listing and house rules guide so that temporary residents/tenants know what to expect. | 3 | 86 | Backlog
87 | As a user, I want to receive push notifications on all of my devices so that I don't miss any important bill alerts, even if the browser is closed. | 5 | 87 | Backlog
88 | As a developer, I want an automated CI/CD pipeline that deploys staging builds to the cloud whenever changes are merged into the main branch, so that integration testing runs continuously. | 5 | 88 | 1
89 | As a roommate, I want to have a record of the utility meter readings and billing statements so that any fluctuations in the electricity and water bills are tracked. | 3 | 89 | Backlog
90 | As a roommate, I would like to be able to report maintenance issues with photos and priority status so that urgent repairs are all tracked and recorded in one place. | 5 | 90 | Backlog
91 | As a roommate, I want an automated move-out security deposit calculator so that any deductions and refunds are split accordingly. | 5 | 91 | Backlog
92 | As a developer, I want API request logging and error tracking through Spluck so that I can monitor and troubleshoot production issues in real-time. | 3 | 92 | Backlog
93 | As a roommate, I want to request temporary quiet times or override existing quiet hours so that roommates can agree on quiet periods when needed. | 2 | 93 | Backlog
94 | As a user, I want recovery codes generated during 2FA setup so that I can regain access to my account if I lose my authentication method. | 3 | 94 | Backlog
95 | As a roommate, I want to archive my completed expenses, settled debts, and finished chores so that active views stay organized and clutter-free. | 2 | 95 | 4
96 | As a grader/new user, I want user documentation and a demo video so that I understand how the app works. | 3 | 96 | 4